## Sheet1
Problem 13:
| Critical Path = A D G J |  |  | Earned value is given by percentage completed * budget
| Activities | Dividing activities based on critical paths.
| A | 150 | 150 | 150 | 150
| B | 100 | 100 | 100
| C |  |  |  |  | 150
| D |  |  |  |  | 75
| E |  |  |  | 100 | 100
| F |  |  |  | 100
G
| H |  |  |  |  | 80
I
J
| EV | 250 | 250 | 250 | 350 | 405
| Cummulative earned value | 250 | 500 | 750 | 1100 | 1505
| Actual costs | 150 | 150 | 450 | 450 | 310
| Cummulative actual costs | 150 | 300 | 700 | 1150 | 1460

## Sheet2
PROBLEM - 14
ACTIVITY | Duration | budget | AC | Complete % | Earned value | CPI | spi
a | 2 | 300 | 400 | 100% | 300 | 0.75 | 1
b | 3 | 200 | 180 | 100% | 200 | 1.1111 | 1
c | 2 | 250 | 300 | 100% | 250 | 0.83333 | 1
d | 5 | 600 | 400 | 20% | 120 | 0.3 | 0.2
e | 4 | 400 | 200 | 20% | 80 | 0.4 | 0.2
|  | 1750 | 1480
Schedule variance == bcwp - bcws |  |  |  | (300+200+250+0.2*600 + 0.2*400 - 300+200+250+.8*600 + 0.5(remaning amount of work on the critical path)*400) = 950(bwcp)-1430(BWCS)
480
cost vaiance = BCWP - ACWP
| 950 - 1480 | 530
cost performance index = 950/1430 |  |  |  | 0.66434
ETC = Estimated time of completion = (1750-950 )/0.664
1204.8193
EAC = ETC + ac(TOTAL)
2684.819