## Before Resource distribution
Sr No | WBS | Tasks | Duration | Predecessors | Team Members | DAYS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 |  | 55 | 56 | 57 | 58
1 | 1 | Certification Project
2 | 1.1 | Application
3 | 1.1.1 | Hiring the consultancy
4 | 1.1.1.1 | Contact the Company | 1 day |  | PM(25%) | DAYS 2: 4
5 | 1.1.1.2 | Finalise the contracts | 2 days | 4 | PM(25%) | DAYS 4: 5
6 | 1.2 | Kickoff Meeting
7 | 1.2.1 | Organize the Kickoff meeting with the consultancy | 1 day | 5 | PM(35%),QE(25%),PE(25%),PC(25%),HD(25%),PL(25%) | DAYS 5: 7
8 | 1.2.2 | Apply for the audit of U-Stamp | 1 day | 7 | PM(20%) + PM(10%) | DAYS 6: 8
9 | 1.3 | Preparation of Quality Control Manual
10 | 1.3.1 | Review of existing methods and operations | 1 day | 5 | PM(75%),QE(65%),PE(40%),PC(40%),HD(50%),PL(25%) - PM(10%) | DAYS 5: 10
11 | 1.3.2 | Quality Chapters | 4 days | 10 | QE(75%) | DAYS 9: 11
12 | 1.3.3 | Design Chapters | 2 days | 10 | HD(60%) | DAYS 7: 12
13 | 1.3.4 | Procurement Chapters | 1 day | 10 | PC(50%) | DAYS 6: 13
14 | 1.3.5 | Production Chapters | 2 days | 10 | PE(25%),PL(25%) | DAYS 7: 14
15 | 1.3.6 | Quality and Production Exhibits | 2 days | 11,14 | QE(75%),PE(25%) | DAYS 11: 15
16 | 1.3.7 | Design Exhibits | 1 day | 12 | HD(50%) | DAYS 8: 16
17 | 1.3.8 | Procurement Exhibits | 1 day | 13 | PC(10%) | DAYS 7: 17
18 | 1.3.9 | Review and Formatting | 1 day | 15,16,17 | PM(35%),QE(25%),PE(25%),PC(25%),HD(25%),PL(25%) | DAYS 12: 18
19 | 1.3.10 | Distribute Uncontrol copies of the manual | 1 day | 18 | PM(10%),QE(5%) | DAYS 13: 19
20 | 1.4 | Audit Meetings
21 | 1.4.1 | Shop Visits | 1 day | 8 | PM(25%),PE(15%),QE(15%) | DAYS 7: 21
22 | 1.4.2 | Meeting 1 | 1 day | 36 | PM(35%),QE(25%),PE(25%),PC(25%),HD(35%),PL(25%) | DAYS 19: 22
23 | 1.4.3 | Review | 1 day | 22 | PM(40%),HD(40%) + HD(30%) | DAYS 20: 23
24 | 1.4.4 | Meeting 2 | 1 day | 44 | PM(35%),QE(35%),PE(25%),PC(35%),HD(25%),PL(25%) - PC(35%) | DAYS 23: 24
25 | 1.4.5 | Review | 1 day | 24 | PM(40%),QE(30%),PE(20%) | DAYS 24: 25
26 | 1.4.6 | Meeting 3 | 1 day | 50,54,55,56,57 | PM(35%),QE(35%),PE(35%),PC(25%),HD(35%),PL(25%) - QE(35%) - PM(35%) + PE(15%) - HD(35%) | DAYS 34: 26
27 | 1.4.7 | Review | 1 day | 26 | PM(40%),QE(30%),PE(30%) - QE(30%) - PM(40%) - PE(30%) | DAYS 35: 27
28 | 1.4.8 | Internal Mock Audit | 3 days | 58 | PM,QE,PE,HD,PL(25%),PC(50%) | DAYS 35: 28
29 | 1.4.9 | Mock Audit | 3 days | 60 | PM,QE,PE,HD,PL(25%),PC(50%) | DAYS 41: 29
30 | 1.4.10 | Review | 1 day | 29 | PM,QE,PE,HD,PL(25%),PC(50%) | DAYS 42: 30
31 | 1.5 | Design of the Model Equipment | [58 empty] | 14 days after 30
32 | 1.5.1 | Finalize dimensions | 1 day | 19 | PM(50%),HD(80%) | DAYS 14: 32
33 | 1.5.2 | Create a CAD Model in 2D and 3D | 1 day | 32 | HD(80%) | DAYS 15: 33
34 | 1.5.3 | Perform software analysis | 2 days | 33 | HD(80%) | DAYS 17: 34
35 | 1.5.4 | Manual Calculations | 3 days | 32 | HD(80%) - HD(60%) + PC(70%) | DAYS 17: 35
36 | 1.5.5 | Final review and stamping | 1 day | 34,35 | PM(50%),HD(80%) + QE(60%) + PC | DAYS 18: 36
37 | 1.6 | Procurement
38 | 1.6.1 | Calcuations in standard sizes | 1 day | 36 | PL(30%) + PC (75%) | DAYS 19: 38
39 | 1.6.2 | Make Purchase Requsition | 1 day | 38 | PL(40%) + PC | DAYS 20: 39
40 | 1.6.3 | Purchase Raw Materials | 3 days | 39 | PC(50%) - PC(37.5%) | DAYS 23: 40
41 | 1.6.4 | Purchase Consumables | 3 days | 39 | PC(50%) - PC(37.5%) | DAYS 23: 41
42 | 1.6.5 | Purchase Asthetic Materials | 6 days | 39 | PC(50%) - PC(37.5%) | DAYS 26: 42
43 | 1.6.6 | Purchase uniform and safety gear | 8 days | 39 | PC(50%) - PC(37.5%) | DAYS 28: 43
44 | 1.6.7 | Hospitality Bookings and Food Araangement on Audit Days | 2 days | 39 | PC(50%) + HD(75%) | DAYS 22: 44
45 | 1.7 | Production
46 | 1.7.1 | Production of Model
47 | 1.7.1.1 | Shell | 4 days | 57 | PE(50%),FW(300%) + QE(28.25%) | DAYS 29: 47
48 | 1.7.1.2 | Dishends | 4 days | 57 | PE(50%),FW(400%) - FW(400%) | DAYS 29: 48
49 | 1.7.1.3 | Nozzles | 4 days | 57 | PE(50%),FW(300%) - PE(50%) | DAYS 29: 49
50 | 1.7.2 | Welding Joints | 2 days | 47,48,49 | PE(50%),FW + PE(50%) | DAYS 31: 50
51 | 1.7.3 | Initial Inspection | 1 day | 50 | PE(50%),FW(200%) | DAYS 32: 51
52 | 1.7.4 | Assembly | 3 days | 51 | PE(50%),FW(400%) - PE(50%) | DAYS 35: 52
53 | 1.8 | Quality |  |  |  | DAYS 35: 45
54 | 1.8.1 | Welder Qualification | 4 days | 19 | QE(75%),FW(200%) - QE(20%) | DAYS 17: 54
55 | 1.8.2 | Instrument Calibration | 3 days | 19 | QE(45%) | DAYS 16: 55
56 | 1.8.3 | Radiography Testing | 2 days | 50 | QE(25%),FW(150%) + FW(50%) -QE(25%) | DAYS 33: 56
57 | 1.8.4 | Raw Material and Consumables Inspection | 2 days | 40,41 | QE,FW(200%) + PE + FW(400%) | DAYS 25: 57
58 | 1.8.5 | Shell, Dishend and Nozzle Inspection | 1 day | 50 | QE,FW(200%) | DAYS 32: 58
59 | 1.8.6 | Welding and Assembly Inspection | 1 day | 52 | QE,FW(200%) + FW(100%) + PM(75%) + PE(65%) + HD(35%) | DAYS 36: 59
60 | 1.8.7 | Final Inspection and Review | 2 days | 59 | QE,PM,PE(40%) | DAYS 38: 60
61 | 1.9 | Final Audit
62 | 1.9.1 | Office and Shop Audit | 0.5 days | 43, 44, 45, 14 days after 30 | PM,QE,PE,HD,PL(25%),PC(50%) | [55 empty] | O | 62
63 | 1.9.2 | Quality Audit | 0.5 days | 62 | PM,QE | [56 empty] | O | 63
64 | 1.9.3 | Procurement Audit | 0.5 days | 62 | PM,PC | [56 empty] | O | 64
65 | 1.9.4 | Production Audit | 0.5 days | 63 | PM,PE,PL(50%),FW(150%) | [57 empty] | O | 65
66 | 1.9.5 | Final Meeting | 0.5 days | 65 | PM,QE,PE,HD,PL,PC | [58 empty] | O
Project Team
|  |  |  | Member Code | Team Member | [59 empty] | Hourly Salary | $per day
|  | 440 | 440 | PM | Project Manager | 0.25 | 0.25 | 0.25 | 1.1 | 0.2 | 0.25 | 0 | 0 | 0 | 0 | 0.35 | 0.1 | 0.5 | 0 | 0 | 0 | 0.5 | 0.35 | 0.4 | 0.35 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 1 | 1.35 | 1.4 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | [14 empty] | 0.5 | 1 | 0.5 | 0.5 | 55 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440
|  | 280 | 280 | QE | Quality Engineer | 0 | 0 | 0 | 0.9 | 0.75 | 0.9 | 0.75 | 0.75 | 0.75 | 0.75 | 0.25 | 0.05 | 1.2 | 1.2 | 1.2 | 0.75 | 0 | 0.25 | 0 | 0.35 | 0.3 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1.25 | 1.25 | 1.35 | 1.3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [14 empty] | 0.5 | 0.5 | 0 | 0.5 | 35 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280
|  | 240 | 240 | PE | Production Engineer | 0 | 0 | 0 | 0.65 | 0.25 | 0.4 | 0 | 0 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 | 0 | 0.25 | 0.2 | 0 | 0 | 0 | 1.5 | 1.5 | 1.5 | 1.5 | 0.5 | 0.5 | 0 | 1.5 | 1.35 | 1.8 | 0 | 0.4 | 0.4 | 1 | 1 | 1 | 1 | [14 empty] | 0.5 | 0 | 0.5 | 0.5 | 30 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240
|  | 240 | 240 | PC | Procurement Coordinator | 0 | 0 | 0 | 0.65 | 0.5 | 0.1 | 0 | 0 | 0 | 0 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 | 0 | 2.85 | 2.5 | 2 | 1 | 1 | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 1 | 0.75 | 0.5 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | [14 empty] | 0.25 | 0.5 | 0 | 0.5 | 30 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240
|  | 360 | 360 | HD | Head Design | 0 | 0 | 0 | 0.75 | 0.6 | 0.6 | 0.5 | 0 | 0 | 0 | 0.25 | 0 | 0.8 | 1.6 | 1.6 | 1.6 | 0.8 | 0.35 | 0.4 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.35 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | [14 empty] | 0.5 | 0 | 0 | 0.5 | 45 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360
|  | 280 | 280 | PL | Planning Engineer | 0 | 0 | 0 | 0.5 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0.55 | 0.4 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 | 0.5 | 0.25 | 0 | 0 | 0 | 0.25 | 0.25 | 0.25 | 0.25 | [14 empty] | 0.125 | 0 | 0.25 | 0.5 | 35 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280
|  | 200 | 200 | FW | Factory Workers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 10 | 10 | 10 | 10 | 3 | 3 | 5.5 | 5.5 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0.75 | 0 | 25 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200
[5 empty] | Cost | 110 | 110 | 110 | 1458 | 764 | 768 | 390 | 210 | 270 | 270 | 504 | 58 | 1244 | 1312 | 1312 | 1186 | 508 | 624 | 432 | 1156 | 908 | 480 | 920 | 920 | 2600 | 2480 | 2480 | 2360 | 720 | 720 | 1670 | 2920 | 2902 | 2762 | 680 | 816 | 816 | 1510 | 1510 | 1510 | 1510 | [14 empty] | 755 | 700 | 560 | 920
[5 empty] | cummulative cost | 110 | 220 | 330 | 1788 | 2552 | 3320 | 3710 | 3920 | 4190 | 4460 | 4964 | 5022 | 6266 | 7578 | 8890 | 10076 | 10584 | 11208 | 11640 | 12796 | 13704 | 14184 | 15104 | 16024 | 18624 | 21104 | 23584 | 25944 | 26664 | 27384 | 29054 | 31974 | 34876 | 37638 | 38318 | 39134 | 39950 | 41460 | 42970 | 44480 | 45990 | 45990 | 45990 | 45990 | 45990 | 45990 | 45990 | 45990 | 45990 | 45990 | 45990 | 45990 | 45990 | 45990 | 45990 | 46745 | 47445 | 48005 | 48925
110

## After resource distribution
Sr No | WBS | Tasks | Duration | Predecessors | Team Members | DAYS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 |  | 55 | 56 | 57 | 58
1 | 1 | Certification Project
2 | 1.1 | Application
3 | 1.1.1 | Hiring the consultancy
4 | 1.1.1.1 | Contact the Company | 1 day |  | PM(25%) | DAYS 2: 4
5 | 1.1.1.2 | Finalise the contracts | 2 days | 4 | PM(25%) | DAYS 4: 5
6 | 1.2 | Kickoff Meeting
7 | 1.2.1 | Organize the Kickoff meeting with the consultancy | 1 day | 5 | PM(35%),QE(25%),PE(25%),PC(25%),HD(25%),PL(25%) | DAYS 5: 7
8 | 1.2.2 | Apply for the audit of U-Stamp | 1 day | 7 | PM(20%) + PM(10%) | DAYS 6: 8
9 | 1.3 | Preparation of Quality Control Manual
10 | 1.3.1 | Review of existing methods and operations | 1 day | 5 | PM(75%),QE(65%),PE(40%),PC(40%),HD(50%),PL(25%) - PM(10%) | DAYS 5: 10
11 | 1.3.2 | Quality Chapters | 4 days | 10 | QE(75%) | DAYS 9: 11
12 | 1.3.3 | Design Chapters | 2 days | 10 | HD(60%) | DAYS 7: 12
13 | 1.3.4 | Procurement Chapters | 1 day | 10 | PC(50%) | DAYS 6: 13
14 | 1.3.5 | Production Chapters | 2 days | 10 | PE(25%),PL(25%) | DAYS 7: 14
15 | 1.3.6 | Quality and Production Exhibits | 2 days | 11,14 | QE(75%),PE(25%) | DAYS 11: 15
16 | 1.3.7 | Design Exhibits | 1 day | 12 | HD(50%) | DAYS 8: 16
17 | 1.3.8 | Procurement Exhibits | 1 day | 13 | PC(10%) | DAYS 7: 17
18 | 1.3.9 | Review and Formatting | 1 day | 15,16,17 | PM(35%),QE(25%),PE(25%),PC(25%),HD(25%),PL(25%) | DAYS 12: 18
19 | 1.3.10 | Distribute Uncontrol copies of the manual | 1 day | 18 | PM(10%),QE(5%) | DAYS 13: 19
20 | 1.4 | Audit Meetings
21 | 1.4.1 | Shop Visits | 1 day | 8 | PM(25%),PE(15%),QE(15%) | DAYS 7: 21
22 | 1.4.2 | Meeting 1 | 1 day | 36 | PM(35%),QE(25%),PE(25%),PC(25%),HD(35%),PL(25%) | DAYS 19: 22
23 | 1.4.3 | Review | 1 day | 22 | PM(40%),HD(40%) + HD(30%) | DAYS 20: 23
24 | 1.4.4 | Meeting 2 | 1 day | 44 | PM(35%),QE(35%),PE(25%),PC(35%),HD(25%),PL(25%) - PC(35%) | DAYS 23: 24
25 | 1.4.5 | Review | 1 day | 24 | PM(40%),QE(30%),PE(20%) | DAYS 24: 25
26 | 1.4.6 | Meeting 3 | 1 day | 50,54,55,56,57 | PM(35%),QE(35%),PE(35%),PC(25%),HD(35%),PL(25%) - QE(35%) - PM(35%) + PE(15%) - HD(35%) | DAYS 34: 26
27 | 1.4.7 | Review | 1 day | 26 | PM(40%),QE(30%),PE(30%) - QE(30%) - PM(40%) - PE(30%) | DAYS 35: 27
28 | 1.4.8 | Internal Mock Audit | 3 days | 58 | PM,QE,PE,HD,PL(25%),PC(50%) | DAYS 35: 28
29 | 1.4.9 | Mock Audit | 3 days | 60 | PM,QE,PE,HD,PL(25%),PC(50%) | DAYS 41: 29
30 | 1.4.10 | Review | 1 day | 29 | PM,QE,PE,HD,PL(25%),PC(50%) | DAYS 42: 30
31 | 1.5 | Design of the Model Equipment | [58 empty] | 14 days after 30
32 | 1.5.1 | Finalize dimensions | 1 day | 19 | PM(50%),HD(80%) | DAYS 14: 32
33 | 1.5.2 | Create a CAD Model in 2D and 3D | 1 day | 32 | HD(80%) | DAYS 15: 33
34 | 1.5.3 | Perform software analysis | 2 days | 33 | HD(80%) | DAYS 17: 34
35 | 1.5.4 | Manual Calculations | 3 days | 32 | HD(80%) - HD(60%) + PC(70%) | DAYS 17: 35
36 | 1.5.5 | Final review and stamping | 1 day | 34,35 | PM(50%),HD(80%) + QE(60%) + PC | DAYS 18: 36
37 | 1.6 | Procurement
38 | 1.6.1 | Calcuations in standard sizes | 1 day | 36 | PL(30%) + PC (75%) | DAYS 19: 38
39 | 1.6.2 | Make Purchase Requsition | 1 day | 38 | PL(40%) + PC | DAYS 20: 39
40 | 1.6.3 | Purchase Raw Materials | 3 days | 39 | PC(50%) - PC(37.5%) | DAYS 23: 40
41 | 1.6.4 | Purchase Consumables | 3 days | 39 | PC(50%) - PC(37.5%) | DAYS 23: 41
42 | 1.6.5 | Purchase Asthetic Materials | 6 days | 39 | PC(50%) - PC(37.5%) | DAYS 26: 42
43 | 1.6.6 | Purchase uniform and safety gear | 8 days | 39 | PC(50%) - PC(37.5%) | DAYS 28: 43
44 | 1.6.7 | Hospitality Bookings and Food Araangement on Audit Days | 2 days | 39 | PC(50%) + HD(75%) | DAYS 22: 44
45 | 1.7 | Production
46 | 1.7.1 | Production of Model
47 | 1.7.1.1 | Shell | 4 days | 57 | PE(50%),FW(300%) + QE(28.25%) | DAYS 29: 47
48 | 1.7.1.2 | Dishends | 4 days | 57 | PE(50%),FW(400%) - FW(400%) | DAYS 29: 48
49 | 1.7.1.3 | Nozzles | 4 days | 57 | PE(50%),FW(300%) - PE(50%) | DAYS 29: 49
50 | 1.7.2 | Welding Joints | 2 days | 47,48,49 | PE(50%),FW + PE(50%) | DAYS 31: 50
51 | 1.7.3 | Initial Inspection | 1 day | 50 | PE(50%),FW(200%) | DAYS 32: 51
52 | 1.7.4 | Assembly | 3 days | 51 | PE(50%),FW(400%) - PE(50%) | DAYS 35: 52
53 | 1.8 | Quality |  |  |  | DAYS 35: 45
54 | 1.8.1 | Welder Qualification | 4 days | 19 | QE(75%),FW(200%) - QE(20%) | DAYS 17: 54
55 | 1.8.2 | Instrument Calibration | 3 days | 19 | QE(45%) | DAYS 16: 55
56 | 1.8.3 | Radiography Testing | 2 days | 50 | QE(25%),FW(150%) + FW(50%) -QE(25%) | DAYS 33: 56
57 | 1.8.4 | Raw Material and Consumables Inspection | 2 days | 40,41 | QE,FW(200%) + PE + FW(400%) | DAYS 25: 57
58 | 1.8.5 | Shell, Dishend and Nozzle Inspection | 1 day | 50 | QE,FW(200%) | DAYS 32: 58
59 | 1.8.6 | Welding and Assembly Inspection | 1 day | 52 | QE,FW(200%) + FW(100%) + PM(75%) + PE(65%) + HD(35%) | DAYS 36: 59
60 | 1.8.7 | Final Inspection and Review | 2 days | 59 | QE,PM,PE(40%) | DAYS 38: 60
61 | 1.9 | Final Audit
62 | 1.9.1 | Office and Shop Audit | 0.5 days | 43, 44, 45, 14 days after 30 | PM,QE,PE,HD,PL(25%),PC(50%) | [55 empty] | O | 62
63 | 1.9.2 | Quality Audit | 0.5 days | 62 | PM,QE | [56 empty] | O | 63
64 | 1.9.3 | Procurement Audit | 0.5 days | 62 | PM,PC | [56 empty] | O | 64
65 | 1.9.4 | Production Audit | 0.5 days | 63 | PM,PE,PL(50%),FW(150%) | [57 empty] | O | 65
66 | 1.9.5 | Final Meeting | 0.5 days | 65 | PM,QE,PE,HD,PL,PC | [58 empty] | O | 66
Project Team
|  |  |  | Member Code | Team Member | [59 empty] | Hourly Salary | $per day
|  | 440 | 440 | PM | Project Manager | 0.25 | 0.25 | 0.25 | 1 | 0.3 | 0.25 | 0 | 0 | 0 | 0 | 0.35 | 0.1 | 0.5 | 0 | 0 | 0 | 0.5 | 0.35 | 0.4 | 0.35 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 1 | 1 | 1 | 0.75 | 1 | 1 | 1 | 1 | 1 | 1 | [14 empty] | 0.5 | 1 | 0.5 | 0.5 | 55 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440
|  | 280 | 280 | QE | Quality Engineer | 0 | 0 | 0 | 0.9 | 0.75 | 0.9 | 0.75 | 0.75 | 0.75 | 0.75 | 0.25 | 0.05 | 1 | 1 | 1 | 0.75 | 0.6 | 0.25 | 0 | 0.35 | 0.3 | 0 | 1 | 1 | 0.2825 | 0.2825 | 0.2825 | 0.2825 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [14 empty] | 0.5 | 0.5 | 0 | 0.5 | 35 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280
|  | 240 | 240 | PE | Production Engineer | 0 | 0 | 0 | 0.65 | 0.25 | 0.4 | 0 | 0 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 | 0 | 0.25 | 0.2 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0.65 | 0.4 | 0.4 | 1 | 1 | 1 | 1 | [14 empty] | 0.5 | 0 | 0.5 | 0.5 | 30 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240
|  | 240 | 240 | PC | Procurement Coordinator | 0 | 0 | 0 | 0.65 | 0.5 | 0.1 | 0 | 0 | 0 | 0 | 0.25 | 0 | 0 | 0.7 | 0.7 | 0.7 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 1 | 0.75 | 0.5 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | [14 empty] | 0.25 | 0.5 | 0 | 0.5 | 30 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240
|  | 360 | 360 | HD | Head Design | 0 | 0 | 0 | 0.75 | 0.6 | 0.6 | 0.5 | 0 | 0 | 0 | 0.25 | 0 | 0.8 | 1 | 1 | 1 | 0.8 | 0.35 | 0.7 | 1 | 0.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0.35 | 0 | 0 | 1 | 1 | 1 | 1 | [14 empty] | 0.5 | 0 | 0 | 0.5 | 45 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360
|  | 280 | 280 | PL | Planning Engineer | 0 | 0 | 0 | 0.5 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0.55 | 0.4 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 | 0.5 | 0.25 | 0 | 0 | 0 | 0.25 | 0.25 | 0.25 | 0.25 | [14 empty] | 0.125 | 0 | 0.25 | 0.5 | 35 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280
|  | 200 | 200 | FW | Factory Workers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0.75 | 0 | 25 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200
[5 empty] | Cost | 110 | 110 | 110 | 1414 | 808 | 768 | 390 | 210 | 270 | 270 | 504 | 58 | 1188 | 1208 | 1208 | 1138 | 916 | 804 | 780 | 982 | 818 | 240 | 1960 | 1960 | 1759.1 | 1639.1 | 1639.1 | 1519.1 | 1440 | 1440 | 1700 | 2830 | 2440 | 2310 | 1492 | 816 | 816 | 1510 | 1510 | 1510 | 1510 | [14 empty] | 755 | 700 | 560 | 920
[5 empty] | cummulative cost | 110 | 220 | 330 | 1744 | 2552 | 3320 | 3710 | 3920 | 4190 | 4460 | 4964 | 5022 | 6210 | 7418 | 8626 | 9764 | 10680 | 11484 | 12264 | 13246 | 14064 | 14304 | 16264 | 18224 | 19983.1 | 21622.2 | 23261.3 | 24780.4 | 26220.4 | 27660.4 | 29360.4 | 32190.4 | 34630.4 | 36940.4 | 38432.4 | 39248.4 | 40064.4 | 41574.4 | 43084.4 | 44594.4 | 46104.4 | 46104.4 | 46104.4 | 46104.4 | 46104.4 | 46104.4 | 46104.4 | 46104.4 | 46104.4 | 46104.4 | 46104.4 | 46104.4 | 46104.4 | 46104.4 | 46104.4 | 46859.4 | 47559.4 | 48119.4 | 49039.4
Project Team
[5 empty] | Member Code | DAYS 1: Team Member; DAYS 2: Average
[5 empty] | PM | DAYS 1: Project Manager; DAYS 2: 0.4
[5 empty] | QE | DAYS 1: Quality Engineer; DAYS 2: 0.594
[5 empty] | PE | DAYS 1: Production Engineer; DAYS 2: 0.46
[5 empty] | PC | DAYS 1: Procurement Coordinator; DAYS 2: 0.42444
[5 empty] | HD | DAYS 1: Head Design; DAYS 2: 0.41
[5 empty] | PL | DAYS 1: Planning Engineer; DAYS 2: 0.11833
[5 empty] | FW | DAYS 1: Factory Workers; DAYS 2: 1.7722
110

## Answers
2 | The entire project is considered as one life cycle. Hence the average number of people required are
Project Team
|  | Member Code | Team Member | Average efficieny |  | Number of people required for the entire project
|  | PM | Project Manager | 40% | 18 | 18
|  | QE | Quality Engineer | 59.4% | 26.73 | 27
|  | PE | Production Engineer | 46% | 20.7 | 21
|  | PC | Procurement Coordinator | 42.44% | 19.1 | 20
|  | HD | Head Design | 41% | 18.45 | 19
|  | PL | Planning Engineer | 11.83% | 5.325 | 6
|  | FW | Factory Workers | 177.2% | 79.75 | 80
3
4
5
From the project, it is observed that the planning engineer are very less in number required to finish the projectwork but they are allocated over a stretch of 58 days which is a waste of resources and time over the Life cycle. For the 9 subtasks, PM is required on an average of 2 people , QE - 3 people, PE- 2 people, PC - 2 people HD- 2 people, PL - 1 person and FW - 9 people. The average efficieny of each person seems to be less than 50% per day apart from the QA. I would improve the average efficienies of each person to be atleast in the range of 70-80 % per day so that the resource will not be wasted and the number of days will be simulataneously reduced which cuts the time on the implementing the entire project.
The average efficieny of each person seems to be less than 50% per day apart from the QA. I would improve the average efficienies of each person to be atleast in the range of 70-80 % per day so that the resource will not be wasted and the number of days will be simulataneously reduced which cuts the time on the implementing the entire project. The s-curve doesnot look like it's supposed to look. The original s-curve doesnot show any lag in the development cycle and is linear in it's growth pattern. In the s-curve that is being generated from the HW, there is a linear development to almost two thirds of the project and then the curve gets stagnated with respect to the cummulative costs. It happens because the task 62 starts after 14 days of finishing the task 30. Hence S-curve looks like a horizontal straight line from days 41 to 55. It represents a miscalculation in terms of the time allocation for the project.
From the matrix division of the organizational continuum, depending on the allocation the staff in the project team can be PM, HD, PE, QE. For these people, the cost per hour is high per day when compared to other departments and for PM and HD considerably less number of people are allocated which suggests that they are on the higher rank. PC, PL might be the staff in the functional team and FW are the staff in the lower chain of the functional team. These assumptions are made based on the cost per hour and the number of people allotted for the project. For example, in the project no resource is allotted after task 30 to task 62 and the days are counted on average. I would go against such wastage of time in order to reduce the days of work to improve the s-curve of the project hence improving the cost saving. Also I would suggest on utilising more number of hours per day of work i,e Planning workers are utilised for 80 percent as soon as their task starts with i,e 6 hours atleast per day at a rate of 35 dollars an hour rather than 1.2 hours per day for a stretch of 58 days which reduces the overall payment per day by almost 40 percent. Hence increasing the efficieny of the project.
By using this tool in order to undrestand the resource allocation of each employee, one can understand how effective the team head is operating or the factory workers are operating on a task. For example if the resource allocation graph of PM and FW are taken, we can draw a conclusion that on days from 23-35, the factory workers work almost a range of 6-people per team for 8 hours where as the project manager works sparingly on an average of 50 percent efficieny. hence we can draw conclusions between the teams, functional vs project lead teams on the hours and management of tasks. This gives a better understanding on the work break down structure of the project life cycle.